## Project Plan
Sprint | Epic | User | US# | US | Task | Point | Hours
| Register and login | SA, FM, C |  | Login | 1. UI Integration 2.Validation 3.Api integration 4.Authorization | 3 | 3
|  | FM |  | Register | 1. UI Integration 2.Validation 3.Api 4.Generate Password Link | 3 | 3
|  | SA, FM, C |  | Reset and forgot password flow | 1.UI Integration 2.api Intergation 3.Authorization | 2 | 2
| Company | SA |  | 1. View company list 2. View - details and stats 3. Update - details only 4. Delete | 1. UI Integration 2.Api integration 3.Sorting with name, 4.Paging 5.Deletion Confirmation 6.Error Message | 5 | 2
|  | FM |  | Update details | 1. UI Integration 2.Api integration 3.Alert For Update | 1 | 1
| Boats | SA, FM, C |  | 1. View list 2. View details | 1. UI Integration 2.API Integration 3.Sorting with name,red impact 4.Paging 5.Deletion Confirmation | 3 | 2
|  | SA |  | 1. View - details and stats 2. Update - details only | 1. UI Integration 2.API Integration 3.Sorting with name 4.Paging 5.Deletion Confirmation 6.Alert For Update
|  | FM |  | 1. View - details and stats 2. Create 3. Update - details only 4. Delete | 1. UI Integration 2.API Integration 3.Sorting with name, 4.Paging 5.Deletion Confirmation 6.Alert For Update
| Captains | SA, FM, C |  | View list | 1. UI Integration 2.API Integration 3.Sorting with name 4.Paging 5.Deletion Confirmation
|  | SA |  | 1. View - details and stats 2. Update - details only | 1. UI Integration 2.API Integration 3.Sorting with name, 4.Paging 5.Deletion Confirmation 6.Alert For Update
|  | FM |  | 1. View - details and stats 2. Create 3. Update - details only 4. Delete | 1. UI Integration 2.Api integration 3.Sorting with name, 4.Paging 5.Deletion Confirmation 6.Add to Database
|  | C |  | 1. View - details and stats 2. Update - details only | 1. UI Integration 2.API Integration 3.Alert For Update
| Help | SA, FM, C |  | View list | 1. UI Integration 2.Api integration
|  | SA |  | View and respond to feedback | 1. UI Integration 2.Api integration 3.Sorting with date,red impact 4.Paging 5.Reply Message
|  | FM, C |  | 1. View list of their Help 2. Send Help | 1. UI Integration 2.Api integration
| Trips | SA, FM, C |  | View list | 1. UI Integration 2.Api integration 3.Sorting with date,boat 4.Paging
|  | SA, FM, C |  | View trip report 1. Details - Captain, boat, duration, avg. speed, max speed, avg. recommended speed, avg. s/r, red impact count, avg. impact, max impact, avg. wind speed, avg. temp., avg. wave height 2. Chart - speed - bar - recommended speed - line - wind speed - line - max impact - line - avg. impact - line - impact - bar 3. Route - Route of boat with start point, end point and direction | 1. UI Integration 2.Api integration 3.Sorting with date,captian,boat, 4.Paging 5.Use of Google maps 6.Use of Chart js
| Dashboard | SA, FM, C |  | View live trips 1. Details - Today's trips, today's red impact count, avg. s/r, peak impact, temp., wind speed, wind dir., wave height 2. On going trip list - Trip ID, Start time, duration, boat, captain, avg. s/r, total red impact count, route 3. Live route - Route of boat with start point, current location and direction - FM and Captains can see their company's trips only | 1. UI Integration 2.Api integration 3.Sorting with date,captian,boat,red impacts 4.Paging 5.Use of Google maps 6.Use of Chart js
| Sidemenu | SA, FM, C |  | Menu items, 1. Dashboard 2. Company 3. Trips 4. Captains 5. Boats 6. Help | 1. UI Integration
| Profile | SA, FM, C |  | View profile, 1. Name 2. Email 3. Password 4. Photo | 1. UI Integration 2.Api Integration

## APIs
# | Feature | API | Owner
1 | Registration | register
2 | Login | verify login
3 | Password | reset password
4 | User | verify user by email
5 |  | get user profile
6 |  | update user profile
7 | Company | edit company
8 |  | get company
9 |  | delete company
10 |  | get company list
11 | Boats | get boat
12 |  | edit boat
13 |  | delete boat
14 |  | get boat list
15 |  | boat statistics
16 | Captains | get captain
17 |  | edit captain
18 |  | delete captain
19 |  | get captain list
20 |  | captain statistics
21 | Trips | create trip
22 |  | update trip
23 |  | dashboard get ongoing trip list
24 |  | dashboard ongoing trip data
25 |  | end trip
26 |  | upload trip data
27 |  | get trip data
28 |  | delete trip
29 |  | get completed trip list
30 |  | trip statistics
31 | Help | create help
32 |  | reply help
33 |  | delete help
34 | Weather | get weather data

## Screens
# | Screens
1 | Login
2 | Register
3 | Reset password
4 | Dashboard
5 | Company list
6 | Company details
7 | Trip list
8 | Trip report
9 | Boat list
10 | Boat details
11 | Captain list
12 | Captain details
13 | Help list
14 | Help details
15 | Profile
16 | Confirmation dialog

## Other Details
Bootstrap | https://startbootstrap.com/themes/sb-admin-2/
https://getbootstrap.com/docs/4.4/examples/
Google Maps | https://developers.google.com/maps/documentation/javascript/examples#drawing-on-the-map
https://www.w3schools.com/graphics/google_maps_overlays.asp
Weather API | stormglass.io
Email | Sendgrid
Charts | Chartjs
Postman
DB design
Architecture
Trip data | Jainam will provide

## Dummy Chart Data
X axis | Y axis
Time | Speed | Reco. speed | Impact | max impact | Wind speed
3:01 | 34 | 32 | 0.8 | 1.5 | 10
3:02 | 32 | 32 | 2.1 | 3 | 15
3:03 | 30 | 32 | 1.2 | 1.9 | 11
3:04 | 30 | 32 | 1.3 | 2 | 19
3:05 | 30 | 32 | 1 | 1.5 | 13
3:06 | 31 | 32 | 1.2 | 1.8 | 12
3:07 | 31 | 32 | 1.7 | 2.5 | 10
3:08 | 31 | 32 | 1.2 | 1.9 | 16
3:09 | 32 | 32 | 1.4 | 2.2 | 14
3:10 | 32 | 32 | 1.5 | 2.6 | 18
3:11 | 32 | 32 | 2.5 | 3.5 | 15
3:12 | 31 | 30 | 1.2 | 1.9 | 11
3:13 | 28 | 30 | 1.7 | 3.1 | 17
3:14 | 27 | 30 | 2.2 | 3.9 | 19
3:15 | 26 | 30 | 1.5 | 2.2 | 12
3:16 | 26 | 30 | 1.4 | 2 | 16
3:17 | 26 | 30 | 1.3 | 1.9 | 18
3:18 | 26 | 30 | 1.6 | 2.5 | 15
3:19 | 26 | 30 | 2.3 | 3.4 | 11
3:20 | 25 | 30 | 1.7 | 2.9 | 17
3:21 | 25 | 30 | 1.5 | 2.5 | 14
3:22 | 25 | 30 | 1.4 | 2.2 | 13